## 2024
APPENDIX ON TRACK WORK TO THE NETWORK STATEMENT
Location | Year of implementation | Line section | Account line section number | Required infrastructure capacity | Timing of infrastructure capacity requirement | Speed limit | Priority: 1: Implementation decision made 2: Implementation decision will be made later | Annual plan number
Helsinki: work specified in the maintenance agreement | 2024 | Helsinki | 1101 | The work consists of several work stages, which are planned in cooperation with individual actors. | - | - | 1 | -
Helsinki: replacement of turnouts | 2024 | Helsinki | 1101 | Service breaks on weeknights and at weekends. | - | - | 1 | -
Töölönlahti pumping station | 2024 | Helsinki | 1101 | 10 x 30 h service break on track 220 | 1 January–31 May 2023 service breaks during weekends | - | 1 | -
Repair of Helsinginkatu underpass | 2024 | Helsinki–(Pasila) | 1101 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Hartwall Arena underpass renewal | 2024 | (Pasila)–(Riihimäki) | 1102 | 15 h–3 day track-specific service breaks. | - | 50/80 | 1 | -
Helsinki–Riihimäki, phase 2: Purola–Jokela | 2024 | (Pasila)–(Riihimäki) | 1102 | Planning begins in 2023, and construction in early 2024. | Track reservations on one track. | 80/140 | 1 | VS1514
Helsinki–Riihimäki: catenary maintenance | 2024 | (Pasila)–(Riihimäki) | 1102 | The traffic impact area will be specified two months prior to implementation. When required, the service break can take place more often than once a month so that the necessary maintenance can be carried out. | From 1 January to 31 December Track possession each month on the night between the first non-holiday Monday and Tuesday in Riihimäki at 0:40–3:55 and in Kytömaa at 0:30–4:30. Helsinki–Kerava will be determined on a case-by-case basis. | - | 1 | VS446
Kehä III (Main Road 50/Ala-Tikkurilantie) bridge repair | 2024 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds. | - | 50/80 | 1 | -
Pasila–Tikkurila tamping | 2024 | (Pasila)–(Riihimäki) | 1102 | 5 x 10 h track possessions. Coordination with work in Tikkurila. | - | 140 | 1 | -
Helsinki–Tampere renovation, start-up phase | 2024 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds | - | - | 2 | -
Helsinki, replacement of turnout V241 | 2024 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds, probably at least a 12-hour service break. | Will be specified as planning proceeds. Probably a Midsummer service break or similar. | - | 2 | -
Malmi turnout replacements V002, V020, V004, V022 | 2024 | (Pasila)–(Riihimäki) | 1102 | Will be specified as planning proceeds, probably at least a 24-hour Midsummer service break and speed limits 50/80 after the work for a few weeks. | Will be specified as planning proceeds. Probably a Midsummer service break or similar. | 50/80 for a few weeks after the work and retamping | 2 | -
Repair of the Monni railway bridge | 2024 | (Pasila)–(Riihimäki) | 1102 | The current bridge is replaced with culverts. Dismantling the bridge deck requires track reservations on one track. A 80 km/h speed limit will be in effect on the main track for a short period. | Long weekend service break in July | 80 | 2 | -
Helsinki–Riihimäki, phase 2: Kytömaa–Ainola | 2024 | (Pasila)–(Riihimäki) | 1102 | Installation of new turnouts. | April–August 2024 for turnouts V690 (installation in April 2024), V625, V626, V747, V748 and for temporary turnouts (June–August/2024). Requires track reservations on one track lasting more than 24 hours on weekends, including 8-hour reservations on two tracks. | 80
Riihimäki–Lahti: Work required by increase in axle load | 2024 | (Riihimäki)–(Lahti) | 1103 | Will be specified as planning proceeds | - | - | 2 | -
Helsinki–Kirkkonummi: work specified in the maintenance agreement | 2024 | (Pasila)–Kirkkonummi | 1104 | In accordance with a separate plan. | - | - | 1 | -
Kirkkonummentie overpass | 2024 | (Pasila)–Kirkkonummi | 1104 | Full service break lasting 30 hours. Full service break 01:00–04:50 on weekdays. Single-track operations Mon–Thu 22:15–05:40. Single track operations between Fri and Sat 22:15–09:00. Single track operations between Sat and Sun 22:15–09:40. Single track operations between Sun and Mon 23:15–05:40. | 1 January–31 December. | 80 | 1 | -
Leppävaara–Espoo: Espoo City Line (ESKA) | 2024 | (Pasila)–Kirkkonummi | 1104 | Traffic arrangements on line section (Leppävaara)–Kauklahti April–May: 4–6 full service breaks, each lasting 12 hours. Full service breaks from Midsummer. duration 5 weeks. September–October. 4–6 full service breaks during weekends, duration 12 h. | 1 April –31 October | 50 and 80 km/h | 1 | -
Improvements to the stability of the Mankinjoki bridge and its arrival embankments | 2024 | (Pasila)–Kirkkonummi | 1104 | Will be specified as planning proceeds. | - | 80 | 2 | -
The Kirkkonummentie underpass | 2024 | (Pasila)–Kirkkonummi | 1104 | - | 1 January–31 December. | 80 | 2 | -
The Ring Rail Line: work specified in the maintenance agreement. | 2024 | (Huopalahti)–Tikkurila | 1105 | In accordance with a separate plan. | - | - | 1 | VS1253
Kerava–Vuosaari: maintenance work in Savio tunnel | 2024 | Vuosaari–(Kerava) | 1108 | Standard track possession on Mondays 09:45–17:50. | 1 January–31 December. | - | 1 | -
Kirkkonummi–Turku: track and turnout tamping | 2024 | (Kirkkonummi)–(Turku) | 1201 | 8 h track possessions on weeknights. | - | - | 1 | -
Kupittaa–Turku rail project (KUTU): Refurbishment of the River Aurajoki railway bridge and construction of a double track | 2024 | (Kirkkonummi)–(Turku) | 1201 | Kupittaa–Turku closed to train traffic. All trains from Helsinki will terminate at Kupittaa. | 15 August 2022–15 December 2024 | - | 1 | -
Karjaa: replacement of turnouts V0051 and V0053 | 2024 | (Kirkkonummi)–(Turku) | 1201 | - | - | - | 2 | -
Kirkkonummi–Turku: Improving stability in the Inkoo area | 2024 | (Kirkkonummi)–(Turku) | 1201 | Major service breaks (to be specified) | - | 80 | 2 | -
Kirkkonummi–Turku: Rankilanjoki railway bridge | 2024 | (Kirkkonummi)–(Turku) | 1201 | - | - | 80 | 2 | -
Renewal of the Siuntio traffic point and renovation of the underpass | 2024 | (Kirkkonummi)–(Turku) | 1201 | - | - | - | 2 | -
Kupittaa–Turku rail project (KUTU): Construction of the Heikkilä railway yard | 2024 | (Turku)–Uusikaupunki | 1202 | Several service breaks on one or more tracks, to be specified later when the track model has been approved | 1 June 2022–30 December 2024 | - | 1 | -
(Turku)–Uusikaupunki–Hangonsaari partial renovation | 2024 | (Turku)–Hangonsaari | 1202 | Daily 10 h track possessions. | - | - | 2 | VS2018
Turku–Toijala: work specified in the maintenance agreement. | 2024 | (Turku)–(Toijala) | 1203 | 2 x 3 h or 5 h track possessions during the maintenance weeks in spring at night and in autumn. | - | - | 1 | VS2441
Hyvinkää–Hanko electrification | 2024 | (Hyvinkää)–(Karjaa)–Hanko | 1204 | Service breaks at night. Also impacts on passenger trains. | 1 January–31 December. Hyvinkää–Karjaa: 21:30–4:45 | - | 1 | VS1275 and VS1854
Kupittaa–Turku rail project (KUTU): Turku station will be completed to its final form; dismantling of tracks 007, 011–013 and construction of tracks 704 and 705 and platforms 4, 5–6 and maintenance facilities. Building the second block of Koulukatu underpass | 2024 | Turku railway yard | 1207 | Traffic from the Helsinki direction closed. Traffic from the direction of Toijala to tracks 701-703 and 707-710. New platform 1-2 and car loading in use on the station side. | 17 July 2023–9 June 2024 | - | 1 | -
Riihimäki–Tampere standard track possession for maintenance | 2024 | (Riihimäki)–(Tampere) | 1301 | Standard track possessions four times a year between Monday–Friday 10:00–14:00, according to a separate plan. | - | - | 1 | VS2422
Repair of Mustalahti underpass | 2024 | (Tampere)–(Lielahti) | 1302 | Will be specified as planning proceeds | - | - | 1 | VS2458
Tampere–Seinäjoki standard track possession: catenary maintenance | 2024 | (Tampere)–(Seinäjoki) | 1302 | 3 x 2 h or 1 x 4 h, nine work shifts in spring and autumn. | - | - | 1 | VS2442
Renovation and restoration of Tammerkoski railway bridge | 2024 | (Tampere–Lielahti) | 1302 | Single-track operations 3–4 months | - | - | 2 | -
Tampere passenger railway yard renovation, TAHERA | 2024 | Tampere passenger railway yard | 1306 | Tracks r007 and r008 closed to traffic. Changes in track use according to a separate plan. | - | - | 2 | VS1555
Repair of Kalkku underpass | 2024 | (Lielahti)–Kokemäki | 1401 | - | - | - | 1 | -
Lielahti–Kokemäki: maintenance | 2024 | (Lielahti)–Kokemäki | 1401 | 2 x 3 h or 5 h track possessions during the maintenance weeks in spring at night and in autumn. | - | - | 1 | -
Tampere–Pori: Construction of Masiantie underpass | 2024 | (Nakkila–Harjavalta) | 1402 | Pile driving in April: 7 h *8 Move on Midsummer 2024: 19 h full service break | 1 January 2024–31 December 2024 | For one week with 50, followed by another week with 80 | 1 | VS2291
Tampere–Pori: Construction of Suutarinmäentie underpass | 2024 | (Nakkila–Harjavalta) | 1402 | Pile driving in April: 7 h *8 Move on Midsummer 2024: 19 h full service break | 1 January 2024–31 December 2024 | For one week with 50, followed by another week with 80 | 1 | VS2289
Improvement of Tampere–Jyväskylä rail line, phase 1: Extending the effective length of the Torkkeli traffic operating point by approx. 50 m. Construction of third track at the Muurame traffic operating point. | 2024 | (Tampere)–Orivesi–(Jyväskylä) | 1405 | - | 48–72 h service break on Midsummer. Track possessions on Sundays approx. between 2:00 and 8:10 | 3 x 50 and 1 x 140 (in accordance with a separate plan) | 1 | -
Jyväskylä–(Pieksämäki) renovation: renewal of signalling equipment, catenary system work, dismantling of the Lievestuore passenger platform, drainage procedures, rock cuts, areas with soft soil, bridges. | 2024 | (Jyväskylä)–(Pieksämäki) | 1406 | (Jyväskylä)–(Hankasalmi): 9–10 h track possessions on weekdays, 10 x 24 h and 1 x 48 h track possessions | 1 May–30 September. 9–10 h track possessions and a 48 h service break due to a bridge transfer in August. | 80 km/h for a leg of 10 km, within which 50 km/h for a leg of 3–5 km, and several intermittent 50 and 80 km/h limits according to a separate plan. | 1 | -
Jyväskylä–(Pieksämäki) renovation: Jyväskylä railway yard: superstructure work on tracks r041, r042, r013, r004, r047, r022, r001, r002. Turnout replacements V007, V013, V017, V019/021, V023, V025, V033 and V030 and the removal of the turnout V310. | 2024 | Jyväskylä railway yard | 1409 | 1 week/track and turnout. | 1 May–30 September. | A separate plan for speed limits. | 1 | -
Vesanka–Rautpohja: Möykynmäki tunnel excavation into a railway cutting or its renovation. | 2024 | (Haapamäki)–(Jyväskylä) | 1503 | Full service break for 11 months. | - | - | 2 | -
Repair of the Munakka railway bridge | 2024 | (Seinäjoki)–Vaasa | 1505 | 20 h service break | - | 80/50 | 1 | -
Renewal of the Berg sewer | 2024 | (Seinäjoki)–Vaasa–Vaskiluoto | 1505 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Lahti–Kouvola: work specified in the maintenance agreement. | 2024 | (Lahti)–(Kouvola) | 1601 | 7 x 6 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Lahti–Villähde: new junction at Kujala. | 2024 | (Lahti)–(Kouvola) | 1601 | 3–16 h service breaks on south track | Will be specified as planning proceeds | North track 140 during the service break, south track 80 a week after the break | 1 | VS2368
Lahti: Renovation of the Launeenkatu underpass | 2024 | (Lahti)–(Kouvola) | 1601 | Phase 1: track 702 closed for one month Phase 2: tracks 703, 704 and 705 closed to traffic for two months | Will be specified as planning proceeds | - | 2 | VS2255
Juurikorpi–Hamina: ETCS test run | 2024 | (Kouvola)–(Kotka)/(Hamina) | 1602 | 7 h during daytime. | Even weeks’ Tuesdays and Wednesdays or Wednesdays and Thursdays. | - | 1 | -
Kouvola–Kotka/Hamina: work specified in the maintenance agreement. | 2024 | (Kouvola)–(Kotka)/(Hamina) | 1602 | Kouvola–Kotka: 7 x 5 h full service breaks twice a year in spring and autumn. Juurikorpi–Hamina: 7 x 5 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Kouvola–Kotka–Hamina railway project (KOKOHA) | 2024 | (Kouvola)–Juurikorpi–(Kotka)/(Hamina) | 1602 | Repairs of bridges’ approach embankments | Single-track operations for 2 x 1 month and 10 h full service breaks between Ojamaa and Pitkäkallio. Two 52 h full service breaks on the line section Juurikorpi–Hamina
Painting of Jyränkö railway bridge | 2024 | (Lahti)–Heinola | 1604 | Speed limit Sn30 and daily track possessions | Daily 8–10 h track possessions. | Sn30 | 2 | -
Kouvola–Pieksämäki: work specified in the maintenance agreement. | 2024 | (Kouvola)–(Pieksämäki) | 1605 | 7 x 5 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Kouvola–Pieksämäki: Repair of Venekallio, Vuohijärvi and Kulonpalonvuori tunnels | 2024 | (Kouvola)–(Pieksämäki) | 1605 | 8 h weekday service breaks 23:40–7:40 or 3:00–11:00 Sun/Mon–Thu/Fri for a period of 8 weeks. Excavation of tunnel ends will require two 24 h service breaks. | - | - | 2 | -
Kouvola–Kuusankoski superstructure repair | 2024 | (Kouvola)–Kuusankoski | 1606 | 10 h track possessions | - | - | 2 | -
Kouvola–Luumäki renovation project (renovation of the northern track) | 2024 | (Kouvola)–Luumäki | 1701 | Daily 8–10 h track possessions and service breaks at weekends. | - | 80/50 | 1 | -
Kouvola–Luumäki: work specified in the maintenance agreement | 2024 | (Kouvola)–Luumäki | 1701 | Standard track possession on two lines at a time 22.00–01.00 and 03.00–06.00. Service breaks on both tracks 01.00–03.00. | - | - | 1 | -
Kouvola–Luumäki: Change of superstructure on the northern track. | 2024 | (Kouvola)–Luumäki | 1701 | Will be specified as planning proceeds. | - | - | 1 | -
Luumäki–Vainikkala: work specified in the maintenance agreement. | 2024 | (Luumäki)–(Vainikkala) | 1702 | Standard 5-hour track possessions in the nights between Sun and Mon and between Mon and Tue (to be specified later). | - | - | 1 | -
LUIMA (Luumäki–Imatra railway project) | 2024 | (Luumäki)–(Imatra) | 1703 | Luumäki–Imatra: Finalising work and trial runs with higher speeds in 2024. | - | - | 1 | -
Luumäki–Imatra: track and turnout tamping, turnout service and maintenance of the catenary system and signalling equipment | 2024 | (Luumäki)–(Imatra) | 1703 | Coordination with LUIMA | - | - | 1 | -
Imatra–Joensuu: maintenance | 2024 | (Parikkala)–(Joensuu) | 1705 | 2 x 3 h or 5 h track possessions at night during the maintenance weeks in spring and in autumn. Coordinated with the replacement of droppers. | - | - | 1 | -
Parikkala–Joensuu: Syrjäsalmi railway bridge | 2024 | (Parikkala)–(Joensuu) | 1705 | Weekend service break, construction of a new track 24 h | - | 30/50 | 2 | -
Joensuu–Uimaharju: work specified in the maintenance agreement. | 2024 | (Joensuu)–Uimaharju | 1707 | 2–3 h track possessions during 2–3 weeknights. | - | - | 1 | VS2371
Uimaharju–Porokylä: work specified in the maintenance agreement. | 2024 | (Uimaharju)–Porokylä | 1708 | 2–3 h track possessions during 2–3 weeknights. | - | - | 1 | VS2370
Pieksämäki–Joensuu: work specified in the maintenance agreement. | 2024 | (Pieksämäki)–(Joensuu) | 1801 | 7 x 5 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Pieksämäki–Kuopio: work specified in the maintenance agreement. | 2024 | (Pieksämäki)–(Kuopio) | 1804 | 7 x 5 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Raising of speeds on line section Kouvola–Kuopio | 2024 | (Pieksämäki)–(Kuopio) | 1804 | - | - | - | 2 | -
Renovation of Mustamäki tunnel | 2024 | (Pieksämäki)–(Kuopio) | 1804 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Pieksämäki–Kuopio: Repair of Neulamäki underpass and Neulamäki tunnel | 2024 | (Pieksämäki)–(Kuopio) | 1804 | Spring 2024–Midsummer 2024: Between 10 and 20 service breaks, each lasting eight hours. Midsummer full service break lasting four days (96 h). Midsummer 2024–late summer 2024: Between 6 and 12 track possessions, each lasting eight hours. Full service break lasting eight days (192 h) in August–September. Full service break will be followed by between 10 and 12 breaks, each lasting eight hours. | 1 April 2024–30 September 2024 | - | 2 | -
Kuopio–Iisalmi: work specified in the maintenance agreement. | 2024 | (Kuopio)–(Iisalmi) | 1805 | 7 x 5 h full service breaks twice a year in spring and autumn. | - | - | 1 | -
Pieksämäki: new intermediate platforms 3 and 4 | 2024 | Pieksämäki railway yard | 1806 | Tracks r003 and r004 are closed to traffic. Track service breaks are phased to occur one track at a time. |  | - | 2 | -
Transfer of Maaherrankatu underpass in Kuopio | 2024 | Kuopio railway yard | 1808 | Full service break 108 h. | 1–6 August 2024 | - | 1 | -
Kuopio: new Kotkankallio underpass | 2024 | Kuopio railway yard | 1808 | Full service break 48 h. | In connection with the Midsummer service break starting on 20 June. | - | 1 | -
Kuopio freight railway yard and work at the new Maaherrankatu underpass | 2024 | Kuopio railway yard | 1808 | Full service break 60 h. | From 20 June 23:00 to 23 June 11:00 | - | 1 | -
Kokkola–Ylivieska: work specified in the maintenance agreement | 2024 | (Kokkola)–(Ylivieska) | 1901 | Daily 8 h track possessions on two lines at a time. | - | - | 1 | VS2360
Ylivieska–Oulu: work specified in the maintenance agreement. | 2024 | (Ylivieska)–(Oulu) | 1901 | 5h track possessions during the maintenance weeks in spring at night and in autumn. | - | - | 1 | VS2363
Renewal of Ohtuanoja railway bridge | 2024 | (Kokkola)–(Ylivieska)–(Oulu) | 1901 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Renovation/renewal of Saaristonkatu underpass | 2024 | (Kokkola)–(Ylivieska)–(Oulu) | 1901 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Renewal of Sammaloja railway bridge | 2024 | (Kokkola)–(Ylivieska)–(Oulu) | 1901 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Tuomioja–Raahe: renovation | 2024 | (Tuomioja)–Raahe | 1903 | 8–10 h track possessions | - | - | 2 | VS2337
Mäntyniemi underpass. (Construction of bridge and underpass) | 2024 | Ylivieska railway yard | 1905 | 2 x 40 h | 1–31 July | - | 1 | VS2366
Oulu railway yard improvement | 2024 | Oulu railway yard | 1906 | Changes in track access. For example, car-carrier wagon loading is prevented for a couple of months. | - | - | 2 | VS2325
Signalling equipment work and commissioning on line section and traffic operating points related the Northern Finland’s Remote Control Project (POKA) | 2024 | Oulu railway yard | 1906 | In accordance with a separate plan. | - | - | 1 | VS2373
Renewal of Kylmälahti railway bridge | 2024 | (Äänekoski)–(Haapajärvi) | 2001 | Will be specified as planning proceeds | Will be specified as planning proceeds | Will be specified as planning proceeds | 2 | -
Renovation of the Vaalansalmi railway bridge | 2024 | Oulu–Kontiomäki | 2105 | Daily 8–10 h track possessions. | - | - | 1 | -
Oulu–Kemi–Laurila–Tornio: work specified in the maintenance agreement. | 2024 | (Oulu)–(Kemi)–Laurila–(Tornio) | 2201 | 2 x 3 h or 5 h track possessions during the maintenance weeks in spring at night and in autumn. | - | - | 1 | VS2341
Change of superstructure at Oulu–Laurila in 2024–2027. The Oulu–Laurila project also involves the renewal of large bridges and the removal of level crossings. | 2024 | (Oulu)–(Kemi)–Laurila–(Tornio) | 2201 | Daily 10 h track possessions | - | - | 2 | -
Repair of Kuivajoki railway bridge | 2024 | Laurila–Tornio border | 2203 | Daily 10 h track possessions | - | - | 2 | VS2357
Laurila–Tornio–Haparanda: Laurila–Tornio–Tornio border–Haparanda electrification | 2024 | Laurila–Tornio border–Haparanda | 2203 | Daily 10 h track possessions | - | - | 1 | VS2093
Laurila–Tornio–Haparanda: Tornio railway yard | 2024 | Tornio–Haparanda | 2203 | Daily 10 h track possessions + 5 x 24 h (including construction and commissioning of signalling equipment) |  |  | 1
Laurila–Tornio–Haparanda: Renewal of Luikko underpass (conditional) | 2024 | Laurila–Tornio border | 2203 | 10 h daily + bridge dismantling and jacking up 48 h |  |  | 2
Laurila–Tornio–Haparanda: Laurila–Tornio–Haparanda, commissioning of signalling equipment and JKV inspection runs | 2024 | Laurila–Tornio–Haparanda | 2203 | 36 h |  |  | 1
Laurila–Tornio–Haparanda: Torne River railway bridge | 2024 | Tornio–Haparanda | 2203 | Daily 10 h track possessions |  |  | 1
Laurila–Tornio–Haparanda: Haparanda 1524 mm track alterations | 2024 | Tornio–Haparanda | 2203 | Daily 10 h track possessions + 5 x 24 h (including construction and commissioning of signalling equipment) |  |  | 1
Repair of Raudanjoki railway bridge | 2024 | Rovaniemi–Kemijärvi | 2204 | 8–10 h track possessions | - | - | 2 | -
Rivisalmi railway bridge renewal | 2024 | (Kemi)–Ajos | 2206 | Not before 2023, will require a nine-month service break (rail access to Veitsiluoto is closed for the duration of the work) | - | - | 2 | -
Renewal of Suutarilankorva underpass | 2024 | Rovaniemi railway yard | 2212 | 40 h | 1–31 July | - | 1 | VS2365